## RIBBS 3.27
|  | Updated March 27th, 2015 Note: A new "Read Me First" tab has been added to this spreadsheet to explain key information in displayed below. | [25 empty] | 2015-01-01 | 7 | Jan
Key | [27 empty] | 2015-01-31 | 3 | Feb
N/A | = Not Applicable | [26 empty] | 2015-02-01 | 0 | March
C or Completion Date | = Previously Completed | [26 empty] | 2015-02-28
[28 empty] | 2015-03-01 | 144 | April
[28 empty] | 2015-03-31 | 3 | May
|  | Originating |  |  | Destinating |  |  | DPS | [19 empty] | 2015-04-01 | 6 | June
AREA Key | De-Activation Plant | O-Letter | O-Flat | O-Package | D-Letter | D-Flat | D-Package | DPS-Letter | DPS-Flat | Activation Plant | For Deactivated Site |  |  |  |  | For Activated Site |  |  |  |  | 3 Digit Zip | Fast MDF Change Date | Label List Effective Date | Final Date Old Address Reflected on 8125 | Parcel Return Service |  | Notes | 2015-04-30 | 193 | July
SA SA | Abilene CSMPC | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | Austin P&DC | 1020 E Overland Trl | Abilene | TX | 79601 | W22666 | 8225 Cross Park Dr | Austin | TX | 78710 | W22814 | 768 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-25 | Austin TX P&DC |  | 2015-05-01 | 1 | August
SA SA | Abilene CSMPC | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | Midland P&DF | 1020 E Overland Trl | Abilene | TX | 79601 | W22666 | 10000 Loop 40 | Midland | TX | 79711 | W24719 | 769, 795, 796 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-25 | Midland TX P&DF |  | 2015-05-31 | 48 | September
EA EA | Akron P&DC | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Cleveland P&DC | 675 WOLF LEDGES PKWY | Akron | OH | 44309 | X20034 | 2400 Orange Ave | Cleveland | OH | 44101 | X20577 | 442-443, 446-447 | 2015-04-01 | 2015-04-01 | 2015-05-01 |  |  |  | 2015-06-01
CM CM | Asheville P&DF | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Greenville P&DC | 591 Brevard Road | Asheville | NC | 28810 | Y14729 | 204 Fairforest Way | Greenville | SC | 29607 | 004291 | 287-289 | 2015-04-01 | 2015-04-01 | 2015-05-01 |  |  |  | 2015-06-30
CM CM | Athens GA P&DF | C | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | North Metro P&DC | 575 Olympic Dr. | Athens | GA | 30601 | X1C753 | 1605 Boggs Road | Duluth | GA | 30096 | 009310 | 305-306 | Completed | No Change | No Change |  |  |  | 2015-07-01
SA CM | Augusta P&DF | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | N/A | Columbia P&DC | 525 8th St | Augusta | GA | 30901 | X10064 | 2001 Dixiana Rd | West Columbia | SC | 29172 | X23726 | 298 | 2015-07-01 | 2015-07-01 | 2015-07-31 | 2015-07-01 | Columbia SC P&DC |  | 2015-07-31
SA SA | Augusta P&DF | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | N/A | Macon P&DC | 525 8th St | Augusta | GA | 30901 | X10064 | 451 College St | Macon | GA | 31213 | X10767 | 308, 309 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-09-30 | Macon GA P&DC |  | 2015-08-01
SA SA | Beaumont P&DF | C | C | C | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | North Houston TX P&DC | 5815 Walden Rd | Beaumont | TX | 77707 | W22885 | 4600 Aldine Bender Rd | North Houston | TX | 77315 | W24934 | 776, 777 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-07-25 | North Houston TX P&DC |  | 2015-08-31
WA WA | Bemidji CSMPC | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Minneapolis P&DC | 401 IRVINE AVE NW | Bemidji | MN | 56601 | Y24815 | 100 S 1st St | Minneapolis | MN | 55401 | Y25844 | 566 | 2015-07-01 | 2015-07-01 | 2015-08-01 | C | N/A | Already at NDC | 2015-09-01
WA WA | Bend CSMPC | C | C | N/A | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Portland P&DC | 2300 NE 4th St | Bend | OR | 97701 | Z14764 | 715 NW Hoyt St | Portland | OR | 97208 | Z15410 | 977 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013 | 2015-09-30
EA EA | Campton CSMPC | 2015-06-01 | 2015-06-01 | 2015-06-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | N/A | Louisville P&DC | 175 MOUNTAIN PARKWAY SPUR RD | Campton | KY | 41301 | X14505 | 1420 GARDINER LN | Louisville | KY | 40231 | X15638 | 413-414 | 2015-07-01 | 2015-07-01 | 2015-08-01
WA GL | Cape Girardeau P&DF | C | C | C | 2015-04-04 | 2015-04-04 | 2015-01-30 | 2015-04-04 | N/A | Saint Louis P&DC | 475 Kell Farm Dr | Cape Girardeau | MO | 63701 | W16080 | 1720 Market St Rm 3025 | St Louis | MO | 63155 | W17797 | 636-639 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
NE NE | Central Mass P&DC | 2015-01-10 | 2015-01-10 | TBD | 2015-07-25 | N/A | TBD | 2015-07-25 | N/A | Boston P&DC (ltrs only) | 192 Main St. | Shrewsbury | MA | 01546 | EV27659 | 25 Dorchester Ave. | Boston | MA | 02205 | V21507 | 013-017 | 2015-07-01 | 2015-04-01 | 2015-08-01 | N/A | N/A
NE NE | Central Mass P&DC | N/A | N/A | N/A | N/A | 2015-07-25 | N/A | N/A | N/A | Middlesex Esx P&DC (flts only) | 192 Main St. | Shrewsbury | MA | 01546 | EV27659 | 76 Main St. | North Reading | MA | 01889 | V22061 | 013-017 | 2015-07-01 | 2015-07-01 | 2015-08-01 | N/A | N/A
EA EA | Chattanooga P&DC | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | Nashville P&DC | 6050 SHALLOWFORD RD | Chattanooga | TN | 37421 | X25002 | 525 Royal Parkway | Nashville | TN | 37230 | X25565 | 373-374 | 2015-07-01 | 2015-07-01 | 2015-08-01
EA CM | Chattanooga P&DC | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | Atlanta P&DC | 6050 SHALLOWFORD RD | Chattanooga | TN | 37421 | X25002 | 3900 CROWN RD SW | Atlanta | GA | 30304 | X10054 | 307 | 2015-07-01 | 2015-07-01 | 2015-08-01
WA WA | Colorado Springs P&DC | C | C | N/A | C | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Denver P&DC | 3655 E Fountain BLVD | Colorado Springs | CO | 80910 | Z17854 | 7540 E 53rd Pl | Denver | CO | 80266 | Z17853 | 808-810 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
SA SA | Corpus Christi P&DC | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | C | 2015-07-25 | N/A | San Antonio P&DC | 809 Nueces Bay Blvd | Corpus Christi | TX | 78469 | W23343 | 10410 Perrin Beitel Rd | San Antonio | TX | 78284 | W26439 | 779, 783, 784 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-25 | San Antonio TX P&DC
WA WA | Dakota Central P&DF | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Sioux Falls P&DC | 355 15TH ST NW | Huron | SD | 57399 | W1C074 | 4801 N 4TH AVE | Sioux Falls | SD | 57104 | W1B107 | 572 - 575 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Sioux Falls P&DC
EA EA | Dayton P&DC | C | C | C | 2015-07-25 | 2015-07-25 | N/A | 2015-07-25 | N/A | Columbus P&DC | 1111 E. 5th St | Dayton | OH | 45401 | X20775 | 2323 Citygate Dr | Columbus | OH | 43218 | X20642 | 453-455 | 2015-07-01 | 2015-07-01 | 2015-08-01
WA WA | Duluth P&DF | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Saint Paul P&DC | 2800 W MICHIGAN ST | Duluth | MN | 58806 | Y25161 | 3232 Denmark Ave | Saint Paul | MN | 55121 | 013150 | 556-558 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Already at NDC
WA WA | Eau Claire P&DF | C | C | N/A | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Saint Paul P&DC | 3510 Hogarth St | Eau Claire | WI | 54703 | Y17229 | 3232 Denmark Ave | Saint Paul | MN | 55121 | 013150 | 547, 548 | 2015-07-01 | 2015-07-01 | 2015-08-01 | C | N/A | Moved with Orig 2013
WA WA | Elko CSMPC | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Salt Lake City P&DC | 500 ASPEN WAY | Elko | NV | 89801 | Z14400 | 1760 W 2100 S | Salt Lake City | UT | 84199 | Z16257 | 898 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-04-18 | Salt Lake City UT ASF
EA EA | Erie P&DF | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Pittsburgh P&DC | 2108 E 38TH ST | Erie | PA | 16515 | X18264 | 1001 California Ave | Pittsburgh | PA | 15290 | EX1A541 | 163-165 | 2015-04-01 | 2015-04-01 | 2015-05-01
EA EA | Erie P&DF | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Rochester P&DC | 2108 E 38TH ST | Erie | PA | 16515 | X18264 | 1335 JEFFERSON RD | Rochester | NY | 14692 | V15731 | 167 | 2015-04-01 | 2015-04-01 | 2015-05-01
WA WA | Eugene P&DF | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Portland P&DC | 3148 GATEWAY ST | Springfield | OR | 97477 | Z14985 | 715 NW Hoyt St | Portland | OR | 97208 | Z15410 | 974 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | 715 NW Hoyt Street Portland OR 97208
PA WA | Eureka CSMPC | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Medford CSMPC | 337 W CLARK ST | Eureka | CA | 95501 | Z21071 | 2195 SAGE RD | Medford | OR | 97501 | Z15248 | 955 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-18 | 715 NW Hoyt Street Portland OR 97208
CM CM | Fayetteville NC Annex | N/A | N/A | 2015-08-16 | N/A | N/A | TBD | N/A | N/A | Fayetteville P&DC | 2507 Downing Road | Fayetteville Annex | NC | 28312 | 001910 | 301 Green Street, Suite 200 | Fayetteville | NC | 28301 | Y15308 |  | N/A | N/A | N/A
CM CM | Fayetteville P&DC | 2015-07-25 | 2015-07-25 | N/A | TBD | TBD | N/A | TBD | N/A | Charlotte P&DC | 301 Green Street, Suite 200 | Fayetteville | NC | 28301 | Y15308 | 2901 Scott Futrell Dr. | Charlotte | NC | 28228 | 008749 | 283-284, 285 | N/A | 2015-04-01 | N/A
CM CM | Fayetteville P&DC | 2015-04-18 | 2015-04-18 | 2015-04-18 | TBD | TBD | TBD | TBD | N/A | Raleigh P&DC | 301 Green Street, Suite 200 | Fayetteville | NC | 28301 | Y15308 | 1 Floretta Pl. | Raleigh | NC | 27676 | Y16259 |  | N/A | N/A | N/A
CM CM | Florence P&DF | C | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Columbia P&DC | 1901 W Evans Street | Florence | SC | 29501 | X29955 | 2001 Dixiana Road | Columbia | SC | 29172 | X29902 | 295 | Completed | No Change | No Change
GL GL | Fox Valley P&DC | C | C | C | 2015-09-30 | 2015-09-30 | N/A | 2015-09-30 | N/A | So Suburban P&DC | 3900 Gabrielle Lane | Fox Valley | IL | 60599 | EW13018 | 6801 W 73rd St | Bedford Park | IL | 60499 | EW12009 | 605 | N/A | 2015-10-01 | N/A | N/A | N/A
SA SA | Gainesville P&DC | C | C | C | C | 2015-07-25 | C | N/A | N/A | Jacksonville P&DC | 4600 SW 34TH St | Gainesville | FL | 32608 | Y21914 | 1100 Kings Rd | Jacksonville | FL | 32203 | Y22124 | 326, 344 | Completed | No Change | No Change | Completed
GL GL | Gary P&DC | C | C | C | 2015-07-25 | 2015-07-25 | TBD | 2015-07-25 | N/A | So Suburban P&DC | 1499 Martin Luther King Dr | Gary | IN | 46401 | EX12284 | 6801 W 73rd St | Bedford Park | IL | 60499 | EW12009 | 463-464 | N/A | 2015-07-01 | N/A | N/A | N/A
WA WA | Grand Island P&DF | C | C | N/A | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Omaha NE P&DC | 3835 W Old Potash Hwy | Grand Island | NE | 68803 | W1C546 | 1124 Pacific St | Omaha | NE | 68108 | W1A092 | 688, 689 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
SA SA | Grenada CSMPC | C | C | C | C | C | 2015-09-30 | 2015-09-30 | N/A | Jackson P&DC | 2500 Gateway St | Grenada | MS | 38901 | Y13691 | 401 E South St | Jackson | MS | 39201 | Y13800 | 387, 389, 397 | Completed | No Change | No Change | Completed
SA SA | Gulfport P&DF | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | N/A | Mobile P&DC | 10285 Corporate Dr | Gulfport | MS | 39503 | Y13699 | 4538 Shipyard Rd | Mobile | AL | 36675 | Y10806 | 395 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-09-30 | Mobiile AL P&DC
SA SA | Hattiesburg CSMPC | C | C | C | 2015-07-25 | C | 2015-07-25 | 2015-07-25 | N/A | Mobile P&DC | 220 S 40th Ave | Hattiesburg | MS | 39402 | Y13720 | 4538 Shipyard Rd | Mobile | AL | 36675 | Y10806 | 394 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-25 | Mobiile AL P&DC
SA SA | Houston P&DC | C | C | 2015-05-12 | 2015-04-18 | 2015-05-16 | 2015-05-12 | 2015-04-18 | N/A | North Houston TX P&DC | 401 Franklin St | Houston | TX | 77201 | W24129 | 4600 Aldine Bender Rd | North Houston | TX | 77315 | W24934 | 770, 772 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-07-25 | North Houston TX P&DC
SA SA | Huntsville P&DF | C | C | C | C | C | C | 2015-07-25 | N/A | Birmingham P&DC | 3408 Wall Triana Hwy | Huntsville | AL | 35813 | Y10631 | 351 24TH St N | Birmingham | AL | 35203 | Y10113 | 356, 357, 358 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-25 | Birmingham AL P&DC
PA PA | Industry P&DC | N/A | N/A | N/A | 2015-04-18 | N/A | N/A | 2015-04-18 | N/A | Santa Ana P&DC (letters) | 15421 E. Gale Ave, City of Industry, CA 91715-9810 | City Of Industry | CA | 91715 | EZ24135 | 3101 W Sunflower, Santa Ana, 92799-9430 | Santa Ana | CA | 92799 | EZ22855 | 906, 917, 918 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-10-01 | Anaheim, CA
PA PA | Industry P&DC | N/A | N/A | 2015-09-30 | N/A | 2015-04-18 | 2015-09-30 | N/A | N/A | Anaheim P&DC (flats) | 15421 E. Gale Ave, City of Industry, CA 91715-9810 | City Of Industry | CA | 91715 | EZ24135 | 5335 E La Palma Ave, Anaheim, VA 92899-9403 | Anaheim | CA | 92899 | EZ24277 | 906, 917, 918 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-10-01 | Anaheim, CA
GL GL | Iron Mountain P&DF | 2015-07-25 | 2015-07-25 | C | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | Green Bay P&DC | 700 W Breitung Ave | Kingsford | MI | 49802 | EY18410 | 300 Packerland Dr | Green Bay | WI | 54303 | EY17374 | 498-499 | N/A | 2015-07-01 | N/A | N/A | N/A
EA EA | Jet Cove Annex | N/A | N/A | 2015-07-25 | N/A | N/A | 2015-07-25 | N/A | N/A | Memphis TN P&DC | 3300 JET CV STE 10 | Memphis | TN | 38118 | 4306 | 555 S. Third St. | Memphis | TN | 38101 | X25496 | 375, 380-383, 386, 388, 723, 724 | 2015-07-01 | 2015-07-01 | 2015-08-01
GL GL | Kalamazoo P&DC | C | C | C | 2015-04-18 | 2015-04-18 | N/A | 2015-04-18 | N/A | Grand Rapids P&DC | 3885 S 9th St | Kalamazoo | MI | 49009 | EY12153 | 225 Michigan St NW | Grand Rapids | MI | 49501 | EY11978 | 490-491 | N/A | 2015-01-01 | N/A | N/A | N/A
GL GL | Kokomo IN P&DF | C | C | C | 2015-04-04 | 2015-04-04 | 2015-04-04 | 2015-04-04 | N/A | Indianapolis P&DC | 2719 S Webster St | Kokomo | IN | 46902 | EX1C317 | 125 W South St | Indianapolis | IN | 46206 | EX12557 | 469 | N/A | 2015-04-01 | N/A | N/A | N/A
WA WA | La Crosse P&DF | C | C | N/A | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Saint Paul P&DC | 425 State Street | La Crosse | WI | 54601 | Y17528 | 3232 Denmark Ave | Saint Paul | MN | 55121 | 013150 | 546 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
GL GL | Lafayette IN P&DF | C | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Indianapolis P&DC | 3450 South St | Lafayette | IN | 47905 | EX12682 | 125 W South St | Indianapolis | IN | 46206 | EX12557 | 479 | N/A | 2015-04-01 | N/A | N/A | N/A
EA EA | Lancaster P&DF | C | C | C | C | 2015-04-18 | N/A | 2015-04-18 | N/A | Harrisburg P&DC | 1400 Harrisburg Pike | Lancaster | PA | 17604 | EX19267 | 1425 Crooked Hill RD | Harrisburg | PA | 17107 | EX18801 | 174-176 | 2015-04-01 | 2015-04-01 | 2015-05-01
GL GL | Lansing P&DC | C | C | C | N/A | N/A | N/A | N/A | N/A | Michigan Metroplex | 4800 Collins Rd | Lansing | MI | 48924 | EY12219 | 711 N Glenwood Ave | Pontiac | MI | 48340 | E010600 | 488-489 | N/A | N/A | N/A | N/A | N/A
GL GL | Lansing P&DC | C | C | 2014-08-06 | 2015-07-25 | 2015-07-25 | N/A | 2015-07-25 | N/A | Grand Rapids P&DC | 4800 Collins Rd | Lansing | MI | 48924 | EY12219 | 225 Michigan St NW | Grand Rapids | MI | 49501 | EY11978 | 488-489 | N/A | PKG 10/1/2014, DEST 7/1/2015 | N/A | N/A | N/A
EA EA | Lexington P&DC | 2015-06-01 | 2015-06-01 | 2015-06-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | 2015-07-01 | N/A | Louisville P&DC | 1088 Nandino Blvd | Lexington | KY | 40511 | X15573 | 1420 GARDINER LN | Louisville | KY | 40231 | X15638 | 403-406 | 2015-07-01 | 2015-07-01 | 2015-08-01
EA EA | Lexington P&DC | C | C | C | C | C | C | N/A | N/A | Knoxville TN P&DC | 1088 Nandino Blvd | Lexington | KY | 40511 | X15573 | 1237 E Weisgarer rd | Knoxville | TN | 37950 | x25384 | 407-409,417-418,425-426 | N/A | N/A | N/A
GL GL | Madison P&DF | 2015-01-05 | 2015-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | Milwaukee P&DC | 3902 Milwaukee St | Madison | WI | 53714 | EY17610 | 345 W St Paul Ave | Milwaukee | WI | 53203 | EY17679 | 535, 537-539 | N/A | 2015-01-01 | N/A | N/A | N/A
SA SA | Manasota P&DC | C | C | C | 2015-09-30 | 2015-09-30 | C | 2015-09-30 | N/A | Fort Myers P&DC | 850 Tallevast Rd | Sarasota | FL | 34260 | Y22324 | 14080 Jetport Loop | Fort Myers | FL | 33913 | Y21885 | 342 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-09-30 | Fort Myers FL P&DC
SA SA | Manasota P&DC | C | C | C | 2015-09-30 | 2015-09-30 | C | 2015-09-30 | N/A | Tampa P&DC | 850 Tallevast Rd | Sarasota | FL | 34260 | Y22324 | 3501 Bessie Coleman Blvd | Tampa | FL | 33630 | Y23078 | 337, 338 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-09-30 | Royal Palm FL P&DC
WA WA | Mankato P&DF | C | C | N/A | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Minneapolis P&DC | 851 Summit Ave | Mankato | MN | 56001 | Y25758 | 100 S 1st St | Minneapolis | MN | 55401 | Y25844 | 560, 561 | 2015-07-01 | 2015-07-01 | 2015-08-01 | C | N/A | Moved with Orig 2013
NE NE | Middlesex Essex P&DC | 2013-04-03 | 2013-04-03 | 2013-04-03 | 2013-10-04 | N/A | N/A | 2013-10-04 | N/A | Boston MA P&DC | 76 Main St. | North Reading | MA | 01889 | V22061 | 25 Dorchester Ave. | Boston | MA | 02205 | V21507 | 018, 019 | N/A | N/A | N/A | N/A | N/A
SA SA | Mid-Florida P&DC | C | C | C | C | C | C | 2015-07-25 | N/A | Orlando P&DC | 800 Rinehart Ave Rd | Mid Florida | FL | 32799 | Y22406 | 10401 Post Office Blvd | Orlando | FL | 32862 | Y22610 | 321, 327 | Completed | No Change | No Change | Completed
NE NE | Mid-Hudson P&DC | 2013-09-07 | 2013-09-07 | N/A | 2013-09-07 | 2013-09-07 | 2013-09-21 | 2015-07-25 | N/A | Albany P&DC | 99 Enterprise Dr. | Newburgh | NY | 12555 | EV14657 | 30 Karner Rd. | Albany | NY | 12288 | EV11841 | 124-127 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-07-25 | Albany P&DC
WA WA | Minot CSMPC | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Bismarck P&DF | 117 5TH AVE SW | Minot | ND | 58701 | W19147 | 2220 E BISMARCK EXPY | Bismarck | ND | 58504 | W18762 | 587, 588 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-04-18 | Bismarck ND P&DF
GL GL | Muncie P&DF | C | C | C | 2015-07-18 | 2015-07-18 | 2015-07-18 | 2015-07-18 | N/A | Indianapolis P&DC | 4300 S Cowan Rd | Muncie | IN | 47302 | EX13027 | 125 W South St | Indianapolis | IN | 46206 | EX12557 | 473 | N/A | 2015-07-01 | N/A | N/A | N/A
SA SA | New Orleans P&DC | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | N/A | Baton Rouge P&DC | 701 Loyola Ave | New Orleans | LA | 70113 | Y24218 | 8101 Bluebonnet Blvd | Baton Rouge | LA | 70810 | Y23369 | 700, 701, 703, 704 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-09-30 | Baton Rouge LA P&DC
WA WA | Norfolk NE P&DF | C | C | N/A | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Omaha NE P&DC | 1100 S Pine Industrial Rd | Norfolk | NE | 68701 | W1A064 | 1124 Pacific St | Omaha | NE | 68108 | W1A092 | 686, 687 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
CM CM | Norfolk P&DC | C | C | C | 2015-07-25 | 2015-07-25 | N/A | N/A | N/A | Richmond P&DC | 600 Church Street | Norfolk | VA | 23501 | X29942 | 5801 Technology Blvd | Sandston | VA | 23150 | 012546 | 233-237 | 2015-07-01 | 2015-07-01 | 2015-08-01
PA PA | North Bay P&DC | C | C | C | 2015-07-25 | C | C | 2015-07-25 | N/A | Oakland P&DC | 1150 N. McDowell Blvd, Petaluma, CA 94999-9702 | Petaluma | CA | 94999 | EZ22186 | 1675 7th, Oakland, CA 94615-9731 | Oakland | CA | 94615 | EZ22295 | 949, 954 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-10-01 | Oakland, CA
NE NE | Northwest Boston P&DF | 2012-10-01 | 2012-10-01 | 2012-10-01 | 2012-10-01 | N/A | 2012-10-01 | 2012-10-01 | N/A | Boston P&DC (ltrs only) | 200 Smith St. | Waltham | MA | 02451 | EV28231 | 25 Dorchester Ave. | Boston | MA | 02205 | V21507 | 020, 023 | N/A | N/A | N/A | N/A | N/A
NE NE | Northwest Boston P&DF | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2015-04-18 | Middlesex Esx P&DC (flts only) | 200 Smith St. | Waltham | MA | 02451 | EV28231 | 76 Main St. | North Reading | MA | 01889 | V22061 | 020, 023 | 2015-07-01 | 2015-04-01 | 2015-08-01 | N/A | N/A
EA EA | Paducah P&DF | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2015-04-01 | N/A | Evansville P&DF | 300 S 4TH ST | Paducah | KY | 42003 | X15987 | 7100 PETERSBURG RD | Evansville | IN | 47711 | X12161 | 420 | 2015-04-01 | 2015-04-01 | 2015-05-01
WA WA | Pendleton CSMPC | C | C | N/A | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Portland P&DC | 104 SW Dorian Ave | Pendleton | OR | 97801 | Z15390 | 715 NW Hoyt St | Portland | OR | 97208 | Z15410 | 978 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
WA WA | Pocatello ID CSMPC | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Salt Lake City P&DC | 1750 FLANDRO DR | Pocatello | ID | 83202 | Z12818 | 1760 W 2100 S | Salt Lake City | UT | 84199 | Z16257 | 832, 834 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-04-18 | Salt Lake City UT ASF
WA WA | Provo CSMPC | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Salt Lake City P&DC | 936 S 250 E | Provo | UT | 84606 | Z17855 | 1760 W 2100 S | Salt Lake City | UT | 84199 | Z16257 | 846 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Salt Lake City UT ASF
WA WA | Provo CSMPC | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Grand Junction CSMPC | 936 S 250 E | Provo | UT | 84606 | Z17855 | 602 BURKEY ST | Grand Junction | CO | 81505 | Z11455 | 845 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Denver MPA Annex
WA WA | Provo CSMPC | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Las Vegas P&DC | 936 S 250 E | Provo | UT | 84606 | Z17855 | 1001 E SUNSET RD | Las Vegas | NV | 89199 | Z18333 | 847 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Las Vegas P&DC
NE NE | Queens P&DC | N/A | N/A | N/A | 2015-07-25 | 2015-04-18 | N/A | 2015-07-25 | N/A | Brooklyn P&DC | 142-02 20th Ave. | Flushing | NY | 11351 | EV13364 | 1050 Forbell St. | Brooklyn | NY | 11256 | EV12316 | 110, 111, 113, 114 | 2015-07-01 | 2015-07-01 | 2015-08-01 | N/A | N/A
PA PA | Redding CSMPC | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | West Sacramento P&DC | 2323 Churn Creek Rd, Redding, CA 96049-9998 | Redding | CA | 96049 | EZ22632 | 3775 Industrial Blvd, West Sacramento, CA 95799-9930 | West Sacramento | CA | 95799 | EZ22760 | 960 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-07-01 | Sacramento, CA
EA CM | Roanoke P&DC | 2015-04-18 | 2015-04-18 | N/A | 2015-07-25 | 2015-07-25 | N/A | 2015-07-25 | N/A | Greensboro P&DC | 419 Rutherford Ave | Roanoke | VA | 24022 | X29910 | 1120 Pleasant Ridge Rd. | Greensboro | NC | 27498 | Y15457 | 240241243245 | 2015-07-01 | 2015-07-01 | 2015-08-01 |  |  | Dest Pkg bundles remain in ROA
WA WA | Rock Springs CSMPC | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Salt Lake City P&DC | 2829 COMMERCIAL WAY | Rock Springs | WY | 82901 | W1B513 | 1760 W 2100 S | Salt Lake City | UT | 84199 | Z16257 | 829-831 | 2015-04-01 | 2015-04-01 | 2015-05-01 | 2015-04-18 | Salt Lake City UT ASF
CM CM | Rocky Mount P&DF | C | C | C | 2015-07-25 | 2015-07-25 | 2015-07-25 | 2015-07-25 | N/A | Raleigh P&DC | 327 E Raleigh Blvd | Rocky Mount | NC | 27801 | Y16330 | 1 Floretta Pl. | Raleigh | NC | 27676 | Y16259 | 275-277
WA WA | Saint Cloud P&DF | C | C | N/A | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Minneapolis P&DC | 517 10th Ave S | Waite Park | MN | 56387 | Y26241 | 100 S 1st St | Minneapolis | MN | 55401 | Y25844 | 562-564 | 2015-07-01 | 2015-07-01 | 2015-08-01 | C | N/A | Moved with Orig 2013
WA WA | Salina KS P&DF | C | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Wichita P&DC | 211 E Ash St | Salina | KS | 67401 | W21349 | 7117 W Harry St | Wichita | KS | 67276 | W21758 | 669, 674 | 2015-04-01 | 2015-04-01 | 2015-05-01 | C | N/A | Moved with Orig 2013
EA EA | Scranton PA P&DF | C | C | C | C | 2015-07-25 | C | 2015-07-25 | N/A | Lehigh Valley PA P&DC | 2800 Stafford Ave | Scranton | PA | 18505 | EX1A956 | 17 S Commerce Way | Lehigh Valley | PA | 18002 | EX19355 | 184-188 | 2015-07-01 | 2015-07-01 | 2015-08-01
WA WA | Seattle WA East DDC | N/A | N/A | N/A | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Seattle P&DC | 7241 185TH AVE NE | Redmond | WA | 98052 | Z17353 | 10700 27th Ave S | Seattle | WA | 98168 | Z17427 | DPS, Carrier Route distribution for select 980, 982 5-digit zones | 2015-07-01 | 2015-07-01 | 2015-08-01 | C | N/A | Already at Seattle
GL GL | South Bend P&DC | 2015-02-14 | 2015-02-14 | 2015-02-14 | 2015-04-01 | 2015-04-01 | 2015-07-25 | 2015-07-25 | N/A | Fort Wayne P&DC | 424 S Michigan St | South Bend | IN | 46601 | EX13618 | 1501 S Clinton St | Fort Wayne | IN | 46802 | EX12224 | 465-466 | N/A | ORIG 4/1/2015, DEST 7/1/2015 | N/A | N/A | N/A
NE NE | Southern Connecticut P&DC | 2013-09-07 | 2013-09-07 | N/A | 2013-09-07 | 2013-09-07 | N/A | 2015-07-25 | N/A | Hartford CT P&DC | 24 Research Pkwy. | Wallingford | CT | 06492 | EV27604 | 141 Weston St. | Hartford | CT | 06101 | EV20284 | 064, 065, 067 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-01-10 | Hartford P&DC
NE NE | Southern Connecticut P&DC | N/A | N/A | N/A | N/A | 2015-04-18 | 2013-05-01 | N/A | N/A | Springfield NDC | 24 Research Pkwy. | Wallingford | CT | 06492 | EV27604 | 190 Fiberloid St. | Springfield | MA | 01152 | KV22551 | 064, 065, 067 | 2015-04-01 | 2015-04-01 | 2015-05-01 | N/A | N/A
CM CM | Southern Maryland | C | C | C | N/A | N/A | N/A | N/A | N/A | Suburban P&DC | 9201 Edgeworth Dr | Capital Heights | MD | 20790 |  | 16501 Shady Grove Rd. | Gaithersburg | MD | 20898
WA WA | Springfield MO P&DF | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Kansas City P&DC | 500 W CHESTNUT EXPY | Springfield | MO | 65801 | W17988 | 1701 Cleveland Ave | Kansas City | MO | 64121 | W1B651 | 648, 654-658 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Kansas City MO P&DC
NE NE | Stamford P&DC | 2013-06-17 | 2013-06-17 | N/A | 2013-09-07 | 2015-01-10 | 2013-09-07 | 2015-07-25 | 2015-01-10 | Westchester NY P&DC | 427 West Ave. | Stamford | CT | 06910 | EV20670 | 1000 Westchester Ave. | White Plains | NY | 10610 | EV19219 | 066, 068-069 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-01-10 | Westchester P&DC
WA WA | Tacoma P&DC | 2015-07-11 | 2015-07-11 | N/A | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Seattle P&DC | 4001 S PINE ST | Tacoma | WA | 98413 | Z17596 | 10700 27th Ave S | Seattle | WA | 98168 | Z17427 | 983-985 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Seattle P&DC
EA GL | Toledo P&DF | C | C | C | N/A | N/A | N/A | N/A | N/A | MI Metroplex P&DC | 435 S Saint Clair St | Toledo | OH | 43601 | x23087 | 711 N GLENWOOD AVE | Pontiac | MI | 48340 | 010600 | 434-436 | N/A | N/A | N/A | N/A | N/A
EA GL | Toledo P&DF | N/A | N/A | N/A | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Detroit P&DC | 435 S Saint Clair St | Toledo | OH | 43601 | x23087 | 1401 W FORT ST | Detroit | MI | 48233 | Y11740 | 434-436 | N/A | 2015-04-01 | N/A | N/A | N/A
EA EA | Toledo P&DF | C | C | C | C | C | C | C | N/A | Columbus P&DC | 435 S Saint Clair St | Toledo | OH | 43601 | x23087 | 2323 Citygate Dr | Columbus | OH | 43218 | X20642 | 458
WA WA | Tucson P&DC | C | C | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Phoenix P&DC | 1501 S Cherrybell | Tucson | AZ | 85726 | Z10944 | 4949 E Van Buren St | Phoenix | AZ | 85026 | Z10745 | 856-857 | 2015-07-01 | 2015-07-01 | 2015-08-01 | C | N/A | Moved with Orig 2013
SA SA | Tulsa P&DC | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | 2015-09-30 | N/A | Oklahoma City P&DC | 2132 S 91ST East Ave | Tulsa | OK | 74141 | W22564 | 4025 W Reno Ave | Oklahoma City | OK | 73125 | 011036 | 740, 741, 743-747, 749 | 2015-10-01 | 2015-10-01 | 2015-11-01 | 2015-09-30 | Oklahoma City OK P&DC
GL GL | Wausau P&DF | C | C | C | 2015-04-18 | 2015-04-18 | 2015-04-18 | 2015-04-18 | N/A | Green Bay P&DC | 400 Creske Ave | Rothschild | WI | 54474 | EY18274 | 300 Packerland Dr | Green Bay | WI | 54303 | EY17374 | 544-545 | N/A | 2015-04-01 | N/A | N/A | N/A
WA WA | Wenatchee CSMPC | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | 2015-07-11 | N/A | Spokane P&DC | 3075 OHME RD | Wenatchee | WA | 98801 | Z17710 | 2928 S Spotted Rd | Spokane | WA | 99224 | Z17490 | 988 | 2015-07-01 | 2015-07-01 | 2015-08-01 | 2015-07-11 | Spokane P&DC
EA EA | Youngstown P&DF | C | C | N/A | C | 2015-07-25 | N/A | 2015-07-25 | N/A | Cleveland P&DC | 99 S. Walnut St | Youngstown | OH | 44501 | X29488 | 2400 Orange Ave | Cleveland | OH | 44101 | X20577 | 444-445 | 2015-07-01 | 2015-07-01 | 2015-08-01

## RIBBS 3.20 to 3.27 Update
Updates from the 3.20.15 Published RIBBS Mail Move Plan
Completed Mail Moves |  |  |  | Completed Consolidation |  |  |  | Date Change |  |  |  |  | Activation Plant Change |  |  | New Mail Moves
De-Activation | Activation | Mail Move | Date | De-Activation | Activation | Consolidation Type | Date | De-Activation | Activation | Mail Move | Original Date | New Date | De-Activation | Original Activation | New Activation | De-Activation | Activation | Mail Move | Date
[8 empty] | South Bend P&DC | Fort Wayne P&DC | D-Package | 2015-06-13 | 2015-07-25
[8 empty] | South Bend P&DC | Fort Wayne P&DC | DPS-Letter | 2015-06-13 | 2015-07-25
[8 empty] | Houston P&DC | North Houston TX P&DC | O-Package | 2015-05-31 | 2015-05-12
[8 empty] | Houston P&DC | North Houston TX P&DC | D-Flat | 2015-04-18 | 2015-05-16
[8 empty] | Houston P&DC | North Houston TX P&DC | D-Package | 2015-05-31 | 2015-05-12
[8 empty] | Central Mass P&DC | Boston P&DC (ltrs only) | D-Letter | 2015-04-18 | 2015-07-25
[8 empty] | Central Mass P&DC | Boston P&DC (ltrs only) | DPS-Letter | 2015-04-18 | 2015-07-25
[8 empty] | Norfolk P&DC | Richmond P&DC | DPS-Letter | 2015-07-25 | N/A
[8 empty] | Augusta P&DF | Columbia P&DC | O-Letter | 2015-07-25 | 2015-09-30
[8 empty] | Augusta P&DF | Columbia P&DC | O-Flat | 2015-07-25 | 2015-09-30
[8 empty] | Augusta P&DF | Columbia P&DC | O-Package | 2015-07-25 | 2015-09-30
[8 empty] | Augusta P&DF | Columbia P&DC | D-Letter | 2015-07-25 | 2015-09-30
[8 empty] | Augusta P&DF | Columbia P&DC | D-Flat | 2015-07-25 | 2015-09-30
[8 empty] | Augusta P&DF | Columbia P&DC | D-Package | 2015-07-25 | 2015-09-30
[8 empty] | Augusta P&DF | Columbia P&DC | DPS-Letter | 2015-07-25 | 2015-09-30